## Munka1
ActivityID | Duration | Requirements | ActivityName
A | 2 |  | Project Start
B | 3 | A | Analysis
C | 4 | A, B | Design
D | 5 | C | Development
E | 2 | C, D | Testing
F | 3 | E | Deployment
G | 4 | F | Maintenance
H | 2 | B | Documentation
I | 3 | H | Project Closure
J | 4 | A, I | Reporting
K | 5 | J | Review
L | 2 | C, G | Quality Control
M | 3 | D, E, H | Performance Test
N | 4 | F, I, L | User Acceptance
O | 5 | J, K, M | Deployment Plan
P | 2 | N, O | Project End